# GENERAL

## RELATED SECTIONS

### Section 01 77 00 - Closeout Procedures.

## SCHEDULES REQUIRED

### Submit schedules as follows:

#### Construction Progress Schedule.

#### Submittal Schedule for Shop Drawings and Product Data.

#### Submittal Schedule for Samples.

#### Product Delivery Schedule.

#### Cash Allowance Schedule for purchasing Products.

#### Shutdown or closure activity.

## FORMAT

### Prepare schedule in form of a horizontal bar chart.

### Provide a separate bar for each major item of work, trade or operation.

### Split horizontally for projected and actual performance.

### Provide horizontal time scale identifying first work day of each week.

### Format for listings: chronological order of start of each item of work.

### Identification of listings: By Systems description.

## SUBMISSION

### Submit initial format of schedules within 15 working days after award of Contract.

### Submit schedules in electronic format, forward on disc as PDF files.

### Submit one opaque reproduction, plus 2 copies to be retained by Owner.

### Owner will review schedule and return review copy within ten (10) working days after receipt.

### Resubmit finalized schedule within seven (7) working days after return of review copy.

### Submit revised progress schedule with each application for payment.

### Distribute copies of revised schedule to:

#### Job site office.

#### Subcontractors.

#### Other concerned parties.

### Instruct recipients to report to Contractor within ten (10) working days, any problems anticipated by timetable shown in schedule.

## CRITICAL PATH SCHEDULING

### Include complete sequence of construction activities.

### Include dates for commencement and completion of each major element of construction as follows.

#### Site clearing.

#### Site utilities.

#### Foundation Work.

#### Structural framing.

#### Special Subcontractor Work.

#### Equipment Installations.

#### Finishes.

### Show projected percentage of completion of each item as of first day of month.

### Indicate progress of each activity to date of submission schedule.

### Show changes occurring since previous submission of schedule:

#### Major changes in scope.

#### Activities modified since previous submission.

#### Revised projections of progress and completion.

#### Other identifiable changes.

### Provide a narrative report to define:

#### Problem areas, anticipated delays, and impact on schedule.

#### Corrective action recommended and its effect.

#### Effect of changes on schedules of other prime contractors.

## SUBMITTALS SCHEDULE

### Include schedule for submitting shop drawings, product data, and samples.

### Indicate dates for submitting, review time, resubmission time, last date for meeting fabrication schedule.

# PRODUCTS (NOT APPLICABLE)

# EXECUTION (NOT APPLICABLE)

END OF SECTION